## Intro
Restaurant Startup Checklist
While every restaurant startup is different and unique, this checklist is designed to help you identify, anticipate and plan for the major and hopefully many of the minor tasks, functions, components and decisions that are part of most new restaurant ventures. You will probably run into issues that are not reflected on this checklist. If so, add these accordingly and please let us know so we can continue to make this as comprehensive as possible. You can email any comments to info@restaurantowner.com or call 623-242-6776. Thanks!
Instructions & Tips:
Before you begin work, save this worksheet and create a working copy using the File, Save As command.
We recommend that you work on each worksheet in the order in which it appears in the tabs below, from left to right.
Copyright © 2012/2013 by RestaurantOwner.com

## By Category
Restaurant Startup Checklist
Countdown to Opening - By Category
Months Before Opening | Category | Activity | Responsible Person/Party | Target Completion Date | Status/Date Competed | Months Before Opening
11 | Administration | Start to interview/build team of professionals - attorney, CPA, architect, designer, insurance agent, real estate broker |  |  |  | 11
10 | Administration | Collect info on permits/licenses - health, liquor, other |  |  |  | 10
10 | Administration | Insurance - identify requirements; building, liability, workmen's comp, other |  |  |  | 10
7 | Administration | Banking - open construction/development account |  |  |  | 7
7 | Administration | Liquor license - investigate application process/availability of liquor license |  |  |  | 7
6 | Administration | Federal ID number - apply for |  |  |  | 6
5 | Administration | Credit application sheet - create for setting up new accounts, include references |  |  |  | 5
4 | Administration | Liquor license - apply for - consider hiring firm to assist in processing application |  |  |  | 4
3 | Administration | Employee meal policy - determine policy |  |  |  | 3
3 | Administration | Employee timekeeping system - decide on stand alone, time cards, manual, POS |  |  |  | 3
2 | Administration | Alcoholic beverage server certification - determine requirements |  |  |  | 2 | 8
2 | Administration | Tax permits - apply for Sales Tax ID (state, local) |  |  |  | 2 | 8
2 | Administration | Banking - open operating, payroll, reserve accounts - order checks, deposit slips |  |  |  | 2 | 7
2 | Administration | Payroll processing - in-house, outsource to ADP, Paychex, outside accountant |  |  |  | 2 | 7
2 | Administration | Credit card merchant accounts - setup for MC/Visa, Amex, Discover, Others |  |  |  | 2 | 6
2 | Administration | Accounting software - if accounting done in-house; Quickbooks, Peachtree, other - format P&L consistent with NRA Uniform System of Accounts |  |  |  | 2 | 5
2 | Administration | Petty cash - setup petty cash fund for cash payments - create petty cash reimbursement form |  |  |  | 2 | 5
2 | Administration | Deposit procedures - armored car service or other |  |  |  | 2 | 4
1 | Administration | Insurance - verify with your agent that all policies are in force |  |  |  | 1 | 4
1 | Administration | Bank supplies - deposit stamp & pad, deposit bags, deposit slips |  |  |  | 1 | 3
1 | Administration | Accounting/bookkeeping system - have CPA review sales, deposit, payroll and accounts payable system |  |  |  | 1 | 2
1 | Administration | Permits, licenses, inspections, approvals - verify that licenses, etc. have been secured |  |  |  | 1 | 2
1 | Administration | Initial change order - get change & small bills from bank |  |  |  | 1 | 1
1 | Administration | POS/merchant accounts - test credit card approval/processing |  |  |  | 1 | 1
1 | Administration | Receive certificate of occupancy |  |  |  | 1 | 1
Administration
Administration
Administration
Administration
Administration
Administration
Restaurant Startup Checklist
Countdown to Opening
Months Before Opening | Category | Activity | Responsible Person/Party | Target Completion Date | Status/Date Competed | Months Before Opening
12 | Concept Development | Examine successful concepts - collect info on concepts that appeal to you |  |  |  | 12
12 | Concept Development | Local market - look for opportunities, concept gaps in your market |  |  |  | 12
12 | Concept Development | Visit existing restaurants - observer which concepts are busy; try to determine why |  |  |  | 12
11 | Concept Development | Menu price range - price points of the most successful restaurants in your area |  |  |  | 11
11 | Concept Development | Preliminary food & bar menus - begin collecting menu & recipe ideas |  |  |  | 11
10 | Concept Development | Further define concept - type of service, price range, menu |  |  |  | 10
9 | Concept Development | Points of difference - what will make your restaurant unique in terms of menu, service, ambiance, other |  |  |  | 9
8 | Concept Development | Concept validation/testing - interview potential customers on your concept plans |  |  |  | 8
8 | Concept Development | Determine name of restaurant - trade name search (attorney) |  |  |  | 8
8 | Concept Development | Finalize concept - menu, service, unique offerings, price range, ambiance, etc. - draft concept statement fully describing concept |  |  |  | 8
Concept Development
Concept Development
Concept Development
Concept Development
Restaurant Startup Checklist
Countdown to Opening - Design & Contruction
Months Before Opening | Category | Activity | Responsible Person/Party | Target Completion Date | Status/Date Competed | Months Before Opening
11 | Design/ Construction | Graphic artist - select graphic artist |  |  |  | 11
9 | Design/ Construction | List of architects - check references, create short list of quality firms |  |  |  | 9
9 | Design/ Construction | List of general contractors - check references, create short list of quality firms |  |  |  | 9
9 | Design/ Construction | List of interior design firms - check references, create short list of quality firms |  |  |  | 9
8 | Design/ Construction | Ansul system - what are local requirements |  |  |  | 8
8 | Design/ Construction | Construction & development costs - get estimates of buildout/construction costs from contractors |  |  |  | 8
8 | Design/ Construction | Exits - panic hardware requirements, emergency lighting - fire code requirements |  |  |  | 8
8 | Design/ Construction | Handicap access/requirements |  |  |  | 8
7 | Design/ Construction | Architectural/design - review & approve |  |  |  | 7
7 | Design/ Construction | Builder's risk insursnce |  |  |  | 7
7 | Design/ Construction | Contractor - select contractor |  |  |  | 7
7 | Design/ Construction | Demolition work |  |  |  | 7
7 | Design/ Construction | Design-Exterior - siding, ramps, windows, awnings, lighting |  |  |  | 7
7 | Design/ Construction | Design-Interior - kitchen, bar, dining room, bar, office, lighting |  |  |  | 7
7 | Design/ Construction | General liability insurance |  |  |  | 7
7 | Design/ Construction | Patio / outside seating - design, available seating, permits, w/w station, cost feasibility |  |  |  | 7
7 | Design/ Construction | Select architect/designer |  |  |  | 7
7 | Design/ Construction | Utilites billing changes - change name/party responsible for utility bills - electrical, gas, water |  |  |  | 7
7 | Design/ Construction | Utilities - determine utility company options - choose provider |  |  |  | 7
6 | Design/ Construction | Acoustical ceilings |  |  |  | 6
6 | Design/ Construction | Air conditioning/circulation |  |  |  | 6
6 | Design/ Construction | Back door - peep hole, buzzer for deliveries, emergency bar |  |  |  | 6
6 | Design/ Construction | Bathroom partitions & accessories |  |  |  | 6
6 | Design/ Construction | Burgler alarm system |  |  |  | 6
6 | Design/ Construction | Canopies & awnings |  |  |  | 6
6 | Design/ Construction | Carpentry |  |  |  | 6
6 | Design/ Construction | Carpet |  |  |  | 6
6 | Design/ Construction | Concrete |  |  |  | 6
6 | Design/ Construction | Construction timeline - time for each phase, completion date |  |  |  | 6
6 | Design/ Construction | Design elements - logo, colors, type style |  |  |  | 6
6 | Design/ Construction | Door locks - deadbolts, re-key locks prior to opening |  |  |  | 6
6 | Design/ Construction | Door/exits hardware - alarms, push bars, emergency escape |  |  |  | 6
6 | Design/ Construction | Doors & Windows |  |  |  | 6
6 | Design/ Construction | Doors, frames & hardware |  |  |  | 6
6 | Design/ Construction | Drywall |  |  |  | 6
6 | Design/ Construction | Electrical/Lighting |  |  |  | 6
6 | Design/ Construction | Exterior painting |  |  |  | 6
6 | Design/ Construction | Flooring - Tile - Resilient - Hardwood - Carpet |  |  |  | 6
6 | Design/ Construction | Interior painting |  |  |  | 6
6 | Design/ Construction | Kitchen fire control - design & setup system |  |  |  | 6
6 | Design/ Construction | List of inspectors - building, fire, electrical, plumbing, health |  |  |  | 6
6 | Design/ Construction | Masonry |  |  |  | 6
6 | Design/ Construction | Mechanical |  |  |  | 6
6 | Design/ Construction | Parking lot - resurfacing, control access during construction |  |  |  | 6
6 | Design/ Construction | Paving |  |  |  | 6
6 | Design/ Construction | Plumbing |  |  |  | 6
6 | Design/ Construction | Resilient flooring |  |  |  | 6
6 | Design/ Construction | Roofing & waterproofing |  |  |  | 6
6 | Design/ Construction | Select contractor - obtain bids - contractor prepares timeline/critical path for completion |  |  |  | 6
6 | Design/ Construction | Smoke detectors - wire to alarm system |  |  |  | 6
6 | Design/ Construction | Sound/music system |  |  |  | 6
6 | Design/ Construction | Specialty items |  |  |  | 6
6 | Design/ Construction | Sprinkler system - obtain requirements - have wired to alarm system |  |  |  | 6
6 | Design/ Construction | Steel/railings |  |  |  | 6
6 | Design/ Construction | Tile - kitchen, bathrooms, dining areas, wall and floor |  |  |  | 6
5 | Design/ Construction | Electrical service - permits, procedures, plans, installation, inspection |  |  |  | 5
5 | Design/ Construction | Gas service - permits, procedures, plans, installation, inspection |  |  |  | 5
5 | Design/ Construction | Grease trap - permits, procedures, plans, installation, inspection |  |  |  | 5
5 | Design/ Construction | Landscaping - design & bid contract |  |  |  | 5
5 | Design/ Construction | Lighting for parking lot |  |  |  | 5
5 | Design/ Construction | Waste water - permits, procedures, plans, installation, inspection |  |  |  | 5
5 | Design/ Construction | Water service - permits, procedures, plans, installation, inspection |  |  |  | 5
4 | Design/ Construction | Water quality - test for hard water, take bids for water softening, filtration |  |  |  | 4
3 | Design/ Construction | Cleaning crew - bid & select vendor for initial & final clean |  |  |  | 3
3 | Design/ Construction | Exterior signage - primary, handicap, reserved, valet, hours of operation, delivery times |  |  |  | 3
3 | Design/ Construction | Supplier, contractor, sub-contractor contacts - create master phone & contact list with emergency numbers |  |  |  | 3
2 | Design/ Construction | Compressors & valves - label and check for accessibility |  |  |  | 2 | 5
2 | Design/ Construction | Electrical labeling - label switches, breakers and check for accessibility |  |  |  | 2 | 5
2 | Design/ Construction | Inspections - schedule for fire, health departments, other |  |  |  | 2 | 4
2 | Design/ Construction | Building & equipment plans - retain full set of plans for operational files |  |  |  | 2 | 6
2 | Design/ Construction | Walk-through with contractor - create initial punch list |  |  |  | 2 | 6
1 | Design/ Construction | Alarm system - install & inspect |  |  |  | 1 | 3
1 | Design/ Construction | Beverage service - set up installation of post mix system, coffee, iced tea |  |  |  | 1 | 3
1 | Design/ Construction | Fire extinguishers - install with visible operating instructions |  |  |  | 1 | 3
1 | Design/ Construction | Exterior signage light timer - set light timer |  |  |  | 1 | 2
1 | Design/ Construction | Update construction punch list |  |  |  | 1 | 2
1 | Design/ Construction | Exterior cleanup - parking lot, landscaping, building, windows |  |  |  | 1 | 1
1 | Design/ Construction | Final clean - interior & exterior of building |  |  |  | 1 | 1
1 | Design/ Construction | Wash windows |  |  |  | 1 | 1
1 | Design/ Construction | Parking lot striping - handicap space requirements |  |  |  | 1 | 4
1 | Design/ Construction | Continue construction punch list |  |  |  | 1 | 1
Design/ Construction
Design/ Construction
Design/ Construction
Design/ Construction
Design/ Construction
Design/ Construction
Design/ Construction
Design/ Construction
Restaurant Startup Checklist
Countdown to Opening - Furniture, Fixtures & Equipment
Months Before Opening | Category | Activity | Responsible Person/Party | Target Completion Date | Status/Date Competed | Months Before Opening
9 | FF&E | Preliminary equipment requirements - create a list of the equipment needed |  |  |  | 9
8 | FF&E | Equipment lists - kitchen, bar, dining room, bar, office |  |  |  | 8
8 | FF&E | Lease or purchase kitchen equipment - shop equipment leasing companies |  |  |  | 8
7 | FF&E | Exterior signage - get local code/permit/approval requirements |  |  |  | 7
4 | FF&E | Safe for office - determine type, bid & order |  |  |  | 4
3 | FF&E | Soda system installation - select vendor & set up installation date |  |  |  | 3
2 | FF&E | Communications/phone system - phone lines for office, fax, kitchen, hostess station - pagers, cell phones, fire & burglar alarms - internet access, service provider |  |  |  | 2 | 8
2 | FF&E | Interior signs - menu boards, restrooms, fire exit, hand wash, wait to be seated |  |  |  | 2 | 8
2 | FF&E | Office equipment - copier, fax, computer, printer, calculators |  |  |  | 2 | 8
2 | FF&E | Office furniture - desk, chairs, filing cabinet, shelving |  |  |  | 2 | 8
2 | FF&E | Receiving scale - minimum 200lb capacity |  |  |  | 2 | 8
2 | FF&E | Restrooms - hand towel/dryer dispensers, soap dispensers, hand soap, baby changing tables |  |  |  | 2 | 6
2 | FF&E | Janitorial equipment - wet floor signs, mops, buckets, vacuum - trash cans, cordless dust pan |  |  |  | 2 | 5
1 | FF&E | Emergency equipment procedures - determine emergency shut-off steps - label equipment |  |  |  | 1 | 4
1 | FF&E | Equipment tests - test each piece with supplier prior to training |  |  |  | 1 | 4
1 | FF&E | Kitchen clock - purchase & install |  |  |  | 1 | 4
1 | FF&E | Kitchen tools/toolkit - purchase & designate location store |  |  |  | 1 | 4
1 | FF&E | Ansul system - inspect |  |  |  | 1 | 3
1 | FF&E | R&M binder for all equipment - prepare repair & maintenance binder for operating instructions, manuals - mail in warranty cards |  |  |  | 1 | 3
1 | FF&E | Storage shelves - clean, organize & label; walk-in, freezer, dry storage |  |  |  | 1 | 3
1 | FF&E | Calibrate temperatures on equipment - fryers, griddle, oven, stove, other |  |  |  | 1 | 2
1 | FF&E | Check walk-in & refrigeration temperatures |  |  |  | 1 | 2
1 | FF&E | Clean & sanitize walk-in, freezer |  |  |  | 1 | 2
1 | FF&E | Receive furniture - tables, chairs, desk tops, benches, patio furniture |  |  |  | 1 | 2
1 | FF&E | Test all equipment |  |  |  | 1 | 2
1 | FF&E | Complete equipment warranty cards |  |  |  | 1 | 1
1 | FF&E | Final clean all equipment |  |  |  | 1 | 1
1 | FF&E | Hang pictures, wall decore |  |  |  | 1 | 1
1 | FF&E | Install interior plants |  |  |  | 1 | 1
1 | FF&E | Run ice machine - empty/sanitize/refill - find ice company for backup |  |  |  | 1 | 1
FF&E
FF&E
FF&E
Restaurant Startup Checklist
Countdown to Opening - Finance & Legal
Months Before Opening | Category | Activity | Responsible Person/Party | Target Completion Date | Status/Date Competed | Months Before Opening
12 | Finance/Legal | Financing - investigate potential sources for startup capital - savings, family, friends, banks, SBA, investors |  |  |  | 12
11 | Finance/Legal | Bank/SBA lending - find banks that have financed restaurant startups |  |  |  | 11
11 | Finance/Legal | Business plan - begin drafting your business plan |  |  |  | 11
11 | Finance/Legal | Capital/construction/opening budget - estimate total startup cost of project through opening day - incorporate this into business plan - refer to Capital Budget worksheet on "Startup & Feasibility Spreadsheets" on RestaurantOwner.com |  |  |  | 11
11 | Finance/Legal | List of possible names for restaurant - solicit ideas from friend, relatives |  |  |  | 11
10 | Finance/Legal | Financial feasibility - begin establishing preliminary financial assumptions - sales, operating costs, capital costs, number of employees, etc. - refer to NRA's Industry Operation's Report for industry averages - use "Startup & Feasibility Spreadsheets" on RestaurantOwner.com |  |  |  | 10
9 | Finance/Legal | Attorney & CPA - find firms with restaurant experience - get & check references |  |  |  | 9
9 | Finance/Legal | Business entity - consider corporation, LLC, partnership, limited partnership - seek guidance from CPA/attorney |  |  |  | 9
9 | Finance/Legal | Personal career accomplishments/work history - prepare and include in business plan |  |  |  | 9
9 | Finance/Legal | Review financial projections with your CPA - have your CPA review for reasonableness, missing costs & expenses - have experienced restaurant professionals review your financials |  |  |  | 9
9 | Finance/Legal | Select attorney - draft/file corporate documents - review/negotiate lease agreement |  |  |  | 9
9 | Finance/Legal | Select CPA - determine corporate entity/review business plan financials |  |  |  | 9
8 | Finance/Legal | Business plan - complete business plan |  |  |  | 8
8 | Finance/Legal | Capital/construction/opening budget - update projections with actual bids/current estimates |  |  |  | 8
8 | Finance/Legal | Personal financial statement - prepare / update your personal financial statement |  |  |  | 8
7 | Finance/Legal | Buy-sell agreement - attorney prepares if you have partners/investors - consider insurance to fund |  |  |  | 7
7 | Finance/Legal | Landlord approvals - determine what items require landlord approval - plans, signage, other |  |  |  | 7
5 | Finance/Legal | Tax ID numbers/accounts - apply for federal, state unemployment insurance, state sales tax |  |  |  | 5
3 | Finance/Legal | Line of credit - set up working capital line of credit with bank |  |  |  | 3
| Finance/Legal |  |  |  |  | 3
| Finance/Legal |  |  |  |  | 3
Finance/Legal
Finance/Legal
Finance/Legal
Finance/Legal
Finance/Legal
| Finance/Legal |  |  |  |  | 3
| Finance/Legal |  |  |  |  | 3
| Finance/Legal |  |  |  |  | 3
Restaurant Startup Checklist
Countdown to Opening - Food & Beverage
Months Before Opening | Category | Activity | Responsible Person/Party | Target Completion Date | Status/Date Competed | Months Before Opening
4 | Food & Beverage | List of available suppliers - create list of suppliers for food, beverages & supplies |  |  |  | 4
3 | Food & Beverage | Beer - decide what bottled / draft beers to stock |  |  |  | 3
3 | Food & Beverage | Food inventory - create master inventory list of all ingredients/products to stock |  |  |  | 3
3 | Food & Beverage | Liquor - determine well/premium/super premium brands |  |  |  | 3
3 | Food & Beverage | Liquor, beer & wine inventory - create inventory worksheets for taking physical inventories - download Inventory Worksheet template on RestaurantOwner.com |  |  |  | 3
3 | Food & Beverage | Price menu - determine final price points on all menu items |  |  |  | 3
3 | Food & Beverage | Standard recipe files - begin building recipe binder & laminated recipe card for menu items - prepare recipe cards for all batch recipes |  |  |  | 3
3 | Food & Beverage | Wine - determine wines to stock |  |  |  | 3
3 | Food & Beverage | Wine list - design & print - include in main menu? |  |  |  | 3
2 | Food & Beverage | HACCAP training / certification - determine local/state certification requirements - arrange for manager/employee certification |  |  |  | 2 | 8
2 | Food & Beverage | Menus - covers & inserts, to-go, catering, children's |  |  |  | 2 | 6
1 | Food & Beverage | Initial food order - prepare & place initial order - request free samples from suppliers to test - have sufficient quantites for testing & training |  |  |  | 1 | 4
1 | Food & Beverage | Photographs of menu items - for display in kitchen area |  |  |  | 1 | 4
1 | Food & Beverage | Initial alcoholic beverage order - prepare & place initial order |  |  |  | 1 | 2
| Food & Beverage |  |  |  |  | 1 | 2
| Food & Beverage |  |  |  |  | 1 | 2
Restaurant Startup Checklist
Countdown to Opening - Marketing
Months Before Opening | Category | Activity | Responsible Person/Party | Target Completion Date | Status/Date Competed | Months Before Opening
9 | Marketing | Competitive analysis - create list of competitors - obtain sample menus for research & reference |  |  |  | 9
4 | Marketing | Menu boards & pictures - determine type, design, order - pictures of key menu items bundled with side & beverage |  |  |  | 4
4 | Marketing | Banners - NOW HIRING /COMING SOON / NOW OPEN |  |  |  | 4
3 | Marketing | Gift certificates - design & print - program gift certificate sales keys into POS (both sale & redemption) |  |  |  | 3
3 | Marketing | Local charities - choose which charity(s) to support - consider a "charity night" pre-opening party |  |  |  | 3
3 | Marketing | Printing - stationary, envelopes, labels, business cards - invitations for opening parties |  |  |  | 3
3 | Marketing | Public relations for opening - hire local PR firm - send out press releases to local media outlets |  |  |  | 3
3 | Marketing | Yellow page ad - determine if yellow page advertising makes sense - inquire about timing of next printing cycle |  |  |  | 3
1 | Marketing | Opening party(s) - press event, VIPs, contractors & suppliers - create guest lists, send invitations |  |  |  | 1 | 4
| Marketing |  |  |  |  | 1 | 4
Marketing
| Marketing |  |  |  |  | 1 | 4
| Marketing |  |  |  |  | 1 | 4
| Marketing |  |  |  |  | 1 | 4
Restaurant Startup Checklist
Countdown to Opening - Ongoing Services
Months Before Opening | Category | Activity | Responsible Person/Party | Target Completion Date | Status/Date Competed | Months Before Opening
5 | Ongoing Services | Insurance agent - building, general liability, liquor liability, workman's comp, group medical |  |  |  | 5
3 | Ongoing Services | Dining room cleaning - carpet, flooring, rest rooms - select outside vendor |  |  |  | 3
3 | Ongoing Services | Hood/kitchen cleaning - select approved vendor |  |  |  | 3
3 | Ongoing Services | Interior plant service - select approved vendor |  |  |  | 3
3 | Ongoing Services | Landscaping/lawn services - select approved vendor |  |  |  | 3
3 | Ongoing Services | Security guards - determine if needed on certain nights/hours |  |  |  | 3
2 | Ongoing Services | Payroll processing - outsource to ADP, Paychex, other |  |  |  | 2 | 8
2 | Ongoing Services | Music - Muzak, ASCAP, BMI (music licensing) - satellite radio |  |  |  | 2 | 7
2 | Ongoing Services | Chemicals - select approved vendor |  |  |  | 2 | 6
2 | Ongoing Services | Grease trap - select approved vendor |  |  |  | 2 | 6
2 | Ongoing Services | Knife & blade sharpening - perform in-house - use outside service |  |  |  | 2 | 6
2 | Ongoing Services | Monthly accounting - determine monthly or 4-week cycle - use industry standard chart of accounts - outside accounting service or in-house bookkeeper/accountant |  |  |  | 2 | 6
2 | Ongoing Services | Pest control - select approved vendor |  |  |  | 2 | 6
2 | Ongoing Services | Trash disposal - select approved vendor |  |  |  | 2 | 6
2 | Ongoing Services | Window washing - do in-house or outsource - select approved vendor |  |  |  | 2 | 6
2 | Ongoing Services | Armored car service - select approved vendor |  |  |  | 2 | 5
2 | Ongoing Services | Building & HVAC repairs - select approved vendors |  |  |  | 2 | 5
2 | Ongoing Services | Dishwasher service - select approved vendor |  |  |  | 2 | 5
2 | Ongoing Services | Laundry & linen - select approved vendor |  |  |  | 2 | 5
1 | Ongoing Services | Equipment repairs - select approved vendors |  |  |  | 1 | 3
1 | Ongoing Services | Equipment repairs - select approved vendors |  |  |  | 1 | 3
| Ongoing Services |  |  |  |  | 1 | 3
Ongoing Services
Ongoing Services
Ongoing Services
Ongoing Services
Ongoing Services
Ongoing Services
| Ongoing Services |  |  |  |  | 1 | 3
| Ongoing Services |  |  |  |  | 1 | 3
| Ongoing Services |  |  |  |  | 1 | 3
| Ongoing Services |  |  |  |  | 1 | 3
Restaurant Startup Checklist
Countdown to Opening - Operations
Months Before Opening | Category | Activity | Responsible Person/Party | Target Completion Date | Status/Date Competed | Months Before Opening
8 | Operations | Visit restaurants with similar offerings - take notes of good & bad items |  |  |  | 8
7 | Operations | Menu & recipes - narrow menu offereings - create & test recipes - use distributor test kitchen if possible |  |  |  | 7
5 | Operations | Table mix & arrangement - determine mix of 2 top, 4 top, round, booths - determine booth / table positions, table numbers |  |  |  | 5
4 | Operations | Hours of operation - determine for each day/meal period |  |  |  | 4
4 | Operations | Vending machines - cigarettes, pay phones, video games, other |  |  |  | 4
3 | Operations | Checklists - prepare opening, closing, shift change checklists for all stations - download checklist templates on RestaurantOwner.com |  |  |  | 3
3 | Operations | Guest (table ready) call system - determine system to use - pagers, sound system, other |  |  |  | 3
3 | Operations | Happy hour - determine special, prices, food - check state/local laws regarding happy hour/discount programs |  |  |  | 3
3 | Operations | Menu analysis - determine items for signature or high promotion status - base decision on gross profit margin, ease of preparation, quality |  |  |  | 3
3 | Operations | Menu item cost - calculate raw food cost on all menu items - rank each categorie's items by gross profit margin - does prime distributor have food management software if so, ask for assistance |  |  |  | 3
3 | Operations | Prep lists with pars - create prep lists with par levels |  |  |  | 3
3 | Operations | Product specs - create detailed product specs for all food products - grade, size, packaging, brand, etc. - ask your distributor for assistance |  |  |  | 3
3 | Operations | Reservation policy - determine if you will take reservations or not - consider "call in" program to place names on wait list only |  |  |  | 3
3 | Operations | Station setup sheets with pars - for kitchen & dining room(s) |  |  |  | 3
2 | Operations | Emergency exit procedures - determine procedures, post maps - discuss in safety meetings with staff |  |  |  | 2 | 7
2 | Operations | Bulletin board - for employee schedule, mandadory postings - choking poster - emergency hospital & doctor numbers & instructions |  |  |  | 2 | 6
2 | Operations | Children's amenities - menu, crayons, coloring book, high chairs, booster seats, balloons |  |  |  | 2 | 6
2 | Operations | Cleaning & maintenance schedules - set up schedules & procedures - download Cleaning Checklists on RestaurantOwner.com |  |  |  | 2 | 6
2 | Operations | Emergency numbers - map, directions to hospital - make arrangements with local doctor, clinic |  |  |  | 2 | 6
2 | Operations | Entertainment - obtain permits if required - create list of potential entertainers |  |  |  | 2 | 6
2 | Operations | Floor maintenance - get ongoing floor maintenance procedures - purchase cleaning / polishing supplies |  |  |  | 2 | 6
2 | Operations | Valet parking - valet stand - key control system - valet only parking area signs, cones |  |  |  | 2 | 6
2 | Operations | Approved vendor list - create Master Approved Vendor List - include primary & backup vendors |  |  |  | 2 | 5
2 | Operations | Birthday specials - determine policy, special desserts, b-day song, other |  |  |  | 2 | 5
2 | Operations | Seating chart & waitstaff sections - create seating chart diagram with waitstaff sections |  |  |  | 2 | 5
2 | Operations | Initial food, beverage & supplies orders - determine quantities for training, mock shifts, pre-opening activities |  |  |  | 2 | 4
1 | Operations | Order & delivery schedule - prepare weekly schedule with each vendor's order & deliver dates - download "Ordering & Receiving Schedule" template on RestaurantOwner.com |  |  |  | 1 | 3
1 | Operations | Padlocks for cooler doors - create control system for access & keys - limit access to storage rooms to deliveries & requisition into production |  |  |  | 1 | 3
1 | Operations | Deposit bags - obtain from bank |  |  |  | 1 | 2
1 | Operations | Hostess stand supplies - reservation book, call clock, pencils, notebooks, kid's stuff |  |  |  | 1 | 2
1 | Operations | Light levels - determine for each meal period - label light switches |  |  |  | 1 | 2
1 | Operations | Change order - prepare initial change order; change & small bills |  |  |  | 1 | 1
1 | Operations | Check inventory levels - on all food, beverage, paper & supplies - prepare orders for opening week |  |  |  | 1 | 1
1 | Operations | Opening inventory - take full physical inventory on all food & beverage items night before opening - necessary to calculate accurate food & beverage costs after opening |  |  |  | 1 | 1
3 | Operations | Customer comment cards - design & print - create procedures for receiving & responding - download template on RestaurantOwner.com |  |  |  | 3
| Operations |  |  |  |  | 3
Operations
Operations
Operations
Operations
Operations
Restaurant Startup Checklist
Countdown to Opening - Personnel
Months Before Opening | Category | Activity | Responsible Person/Party | Target Completion Date | Status/Date Competed | Months Before Opening
4 | Personnel | Employee benefits - determine insurance coverage (medical, dental, life, disability) & eligibility - vacation, meals, comps, tuition reimbursement, other |  |  |  | 4
4 | Personnel | Employee job descriptions - create for all staff & management positions - download templates on RestaurantOwner.com |  |  |  | 4
4 | Personnel | Management team - start interviewing/selection process |  |  |  | 4
4 | Personnel | Organizational chart - create organizational chart for restaurant |  |  |  | 4
3 | Personnel | Employee handbook - create to document and communicate all employee & employment practices - download template on RestaurantOwner.com |  |  |  | 3
3 | Personnel | Employee training manuals - create for all positions - download templates on RestaurantOwner.com |  |  |  | 3
3 | Personnel | Management training materials - personnel hiring, training & management - operations - administrative |  |  |  | 3
3 | Personnel | Master training schedule - create schedule for staffing training leading up to opening day |  |  |  | 3
3 | Personnel | Sidework procedures & schedules - create server/front-of-house sidework checklists - download template on RestaurantOwner.com |  |  |  | 3
3 | Personnel | Staff pay scales - determine starting pay scales for each position - determine employee review/raise policies |  |  |  | 3
3 | Personnel | Staffing needs - determine number of new hires needed by position - plan for turnover, hire 20% more than you think you need |  |  |  | 3
2 | Personnel | Employee recruiting - newspaper ads, "NOW HIRING" banner - recruiting missions - word of mouth campaigns - bonus for referrals - plan for turnover, hire 20% more than you think you need |  |  |  | 2 | 7
2 | Personnel | Pre-opening interview site - trailer, temporary office - equip with phone, furniture, hiring/selection forms |  |  |  | 2 | 7
2 | Personnel | Food safety training - purchase food safety training materials/videos - contact state or National Restauant Association |  |  |  | 2 | 6
2 | Personnel | Assemble new employee materials - application forms - uniforms - W-4, I-9 forms - employee handbook, job descriptions - orientation & training checklists - check RestaurantOwner.com for forms & templates |  |  |  | 2 | 5
2 | Personnel | Employee files - set up for employment application, status changes, other personnel records |  |  |  | 2 | 5
1 | Personnel | OSHA - review OSHA standards with managers |  |  |  | 1 | 4
1 | Personnel | Alcoholic beverage server certification - determine state/local requirements - assign employee(s) for certification course |  |  |  | 1 | 3
1 | Personnel | HACCAP training / certification - assign employee(s) for certification course |  |  |  | 1 | 3
1 | Personnel | Safety checklist & audit - create safety checklist & perform safety audit - download Safety Checklist template on RestaurantOwner.com |  |  |  | 1 | 3
1 | Personnel | Wine training program - arrange for wine supplier to provide |  |  |  | 1 | 3
1 | Personnel | Begin staff training |  |  |  | 1 | 2
1 | Personnel | Safety & first aid training - conduct training program for all employees |  |  |  | 1 | 2
1 | Personnel | Conduct practice runs/mock service - full dress with uniforms |  |  |  | 1 | 1
1 | Personnel | Finalize opening week employee schedules - staff heavy - plan for turnover, no-shows |  |  |  | 1 | 1
| Personnel |  |  |  |  | 1 | 1
Restaurant Startup Checklist
Countdown to Opening - Site / Planning
Months Before Opening | Category | Activity | Responsible Person/Party | Target Completion Date | Status/Date Competed | Months Before Opening
12 | Site/Planning | Potential of local markets - become familiar with local markets that show potential for new restaurants - create short list of the most promising areas |  |  |  | 12
10 | Site/Planning | Facility requirements - how much space, seats, parking will you need |  |  |  | 10
10 | Site/Planning | Site/location criteria - determine site/location criteria - demographics, traffic count - size, number of seats, rental rates - lease terms - other |  |  |  | 10
9 | Site/Planning | Competitive analysis - examine strengths & weaknesses of competitors in target areas - evaluate relative success of restaurant in local market - where is there potential? - what dining segments are not being well-served? |  |  |  | 9
9 | Site/Planning | Square footage - determine optimum square footage needed (range) - including kitchen, dining room, storage - rule of thumb is roughly 30 square feet per seat (total square footage) |  |  |  | 9
9 | Site/Planning | Tenent rep broker - secure service of a tenent rep broker to assist you in site selection - find a broker with a specialty or focus on restaurant sites |  |  |  | 9
8 | Site/Planning | Bar seating - estimate potential for bar revenue - balance with space/seating needed for dining room |  |  |  | 8
8 | Site/Planning | Building/fire/safety codes - obtain all applicable code requirements |  |  |  | 8
8 | Site/Planning | Electrical service - evaluate adequacy of available power |  |  |  | 8
8 | Site/Planning | Floor plan (existing space) - obtain floor plan of space - include layout of load-bearing (permanent) walls |  |  |  | 8
8 | Site/Planning | Floor slope evaluation - consider slope on handicap, OSHA requirements - safety considerations for staff & guests |  |  |  | 8
8 | Site/Planning | Lighting fixtures - inspect interior & exterior lighting including parking lot |  |  |  | 8
8 | Site/Planning | Liquor license - know the process & cost of obtaining a liquor license |  |  |  | 8
8 | Site/Planning | List of existing kitchen equipment - obtain detailed list - verify & evaluate condition |  |  |  | 8
8 | Site/Planning | Number of tables/seats - estimate potential seating/revenue potential of dining room |  |  |  | 8
8 | Site/Planning | Parking - is there adequate parking - what is the ratio of seats to parking spaces, is there a local minimum |  |  |  | 8
8 | Site/Planning | Sales to investment analysis - estimate total capital costs & compare to projected annual sales - goal is to have minimum 1.5 to 1 sales to investment ratio in leasehold - goal is to have minimum 1 to 1 ratio when land & building is owned - go to RestaurantOwner.com for more information |  |  |  | 8
8 | Site/Planning | Traffic patterns - evaluate adequacy of traffic flow (foot traffic, if applicable) |  |  |  | 8
8 | Site/Planning | Zoning requirements - verity that there are no zoning problems with your concept/plans |  |  |  | 8
7 | Site/Planning | Cleanup required - determine cost of cleanup/demolition prior to construction activities |  |  |  | 7
7 | Site/Planning | Gas main / lines - adequate size, capacity, age, condition |  |  |  | 7
7 | Site/Planning | Health department - verify no health-related conditions present that could pose problems |  |  |  | 7
7 | Site/Planning | HVAC system - inspect/evaluate condition |  |  |  | 7
7 | Site/Planning | Plans for location/site area - inquire with local officials about proposed, planned projects in area - road, water, sewer, drainage, commercial, residential, zoning changes |  |  |  | 7
7 | Site/Planning | Roof inspection |  |  |  | 7
7 | Site/Planning | Sewer lines - evaluate adequacy; size, capacity, age, condition |  |  |  | 7
7 | Site/Planning | Termite report - have property inspected for termite/pest problems |  |  |  | 7
7 | Site/Planning | Type of flooring |  |  |  | 7
7 | Site/Planning | Utility requirements - verify no utility/capacity problems |  |  |  | 7
7 | Site/Planning | Water lines - evaluate capacity, size, age, condition |  |  |  | 7
6 | Site/Planning | Site selection decision - finalize site selection |  |  |  | 6
Site/Planning
Site/Planning
Site/Planning
Site/Planning
Site/Planning
Site/Planning
Site/Planning
Site/Planning
| Site/Planning |  |  |  |  | 6
| Site/Planning |  |  |  |  | 6
| Site/Planning |  |  |  |  | 6
| Site/Planning |  |  |  |  | 6
| Site/Planning |  |  |  |  | 6
| Site/Planning |  |  |  |  | 6
Restaurant Startup Checklist
Countdown to Opening - Smallwares / Supplies
Months Before Opening | Category | Activity | Responsible Person/Party | Target Completion Date | Status/Date Competed | Months Before Opening
3 | Smallwares/ Supplies | Uniforms - finalize design; kitchen, service, bar, host staffs, managers |  |  |  | 3 | 12
2 | Smallwares/ Supplies | Dishroom items - bus carts, bus tubs, glass racks, tray racks - chemicals, detergents |  |  |  | 2 | 8
2 | Smallwares/ Supplies | Smallware & kitchen utensils - source, specs, bid order |  |  |  | 2 | 8
2 | Smallwares/ Supplies | Dining room - high chairs - infant cradles - booster seats - water pitchers, wine carafes - serving trays, tray stands |  |  |  | 1 | 3
2 | Smallwares/ Supplies | Bar - blender - ice machine - glass washer - shakers, strainers, spoons, bottle openers, corkscrew - jiggers - scoops - bar mats - pitchers
2 | Smallwares/ Supplies | Tabletop items - tableware, flatware, glassware, sugar caddies, table tents, vases - salt & pepper shakers |  |  |  | 2 | 8
2 | Smallwares/ Supplies | Employee name tags |  |  |  | 2 | 6
2 | Smallwares/ Supplies | First aid kit - emergency burn kit |  |  |  | 2 | 5
2 | Smallwares/ Supplies | Tip trays, check presentation folders - may be free from AMEX/MC or VISA |  |  |  | 2 | 5
1 | Smallwares/ Supplies | Initial chemicals order - degreasers, drain treatment - disinfectants, sanitizers - floor care solutions - handcare - cleaners for dishroom/restroom/dining room |  |  |  | 1 | 4
1 | Smallwares/ Supplies | Linen - table cloths, napkins, bar & kitchen towels |  |  |  | 1 | 4
1 | Smallwares/ Supplies | Initial paper good order - napkins, take-out, delivery, coasters, doggie bags - straws, cups, lids - filters, butcher pager - patty paper, food wrap film, aluminum foil - clear trash can liners |  |  |  | 1 | 3
1 | Smallwares/ Supplies | Janitorial supplies - carpet, tile, floor cleaner, spot remover - gum solvent, liquid hand soap, paper towels, toilet paper - windex, paper towels - "Wet Floor" signs |  |  |  | 1 | 3
| Smallwares/ Supplies |  |  |  |  | 1 | 3
Smallwares/ Supplies
Smallwares/ Supplies
Smallwares/ Supplies
Smallwares/ Supplies
Smallwares/ Supplies
Smallwares/ Supplies
Smallwares/ Supplies
Smallwares/ Supplies
Smallwares/ Supplies
Smallwares/ Supplies
| Smallwares/ Supplies |  |  |  |  | 1 | 3
Restaurant Startup Checklist
Countdown to Opening -Technology
Months Before Opening | Category | Activity | Responsible Person/Party | Target Completion Date | Status/Date Competed | Months Before Opening
3 | Technology | POS phone line - dedicated line for charge approvals - tie into DSL/cable line |  |  |  | 3
3 | Technology | POS system - list requirements - download POS Evaluation Worksheet on Restaurantowner.com - create list of brands/dealers used by other local operaters - start evaluation/demonstration process |  |  |  | 3
3 | Technology | Website - register domain name - contact web design firm |  |  |  | 3
2 | Technology | Computer software - Microsoft office, scheduling, food management |  |  |  | 2 | 7
2 | Technology | POS system - make POS decision - set up menu items & prices - decide on comps & discount categories - set up essential reports |  |  |  | 2 | 7
2 | Technology | Phone on hold message - select service provider - message/music |  |  |  | 2 | 6
1 | Technology | Internet service provider - DSL, cable, satellite |  |  |  | 1 | 4
1 | Technology | POS/register - set up installation & training |  |  |  | 1 | 3
Technology
Technology
Technology
Technology
Technology
Technology
Note on A5: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on G5: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on A41: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on G41: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on A60: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on G60: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on A154: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on G154: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on A192: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on G192: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on A226: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on G226: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on A247: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on G247: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on A266: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on G266: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on A303: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on G303: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on A349: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on G349: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on A380: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on G380: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on A430: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on G430: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on A460: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on G460: Guidelines to begin/complete this activity prior to scheduled opening day.

## By Month
Restaurant Startup Checklist
Countdown to Opening
Months Before Opening | Category | Activity | Responsible Person/Party | Target Completion Date | Status/Date Competed |  |  | Months Before Opening
12 | Concept | Examine successful concepts - collect info on concepts that appeal to you | [5 empty] | 12
12 | Concept | Local market - look for opportunities, concept gaps in your market | [5 empty] | 12
12 | Concept | Visit existing restaurants - observer which concepts are busy; try to determine why | [5 empty] | 12
12 | Finance/Legal | Financing - investigate potential sources for startup capital - savings, family, friends, banks, SBA, investors | [5 empty] | 12
12 | Site/Planning | Potential of local markets - become familiar with local markets that show potential for new restaurants - create short list of the most promising areas | [5 empty] | 12
11 | Administration | Start to interview/build team of professionals - attorney, CPA, architect, designer, insurance agent, real estate broker | [5 empty] | 11
11 | Concept | Menu price range - price points of the most successful restaurants in your area | [5 empty] | 11
11 | Concept | Preliminary food & bar menus - begin collecting menu & recipe ideas | [5 empty] | 11
11 | Design/ Construction | Graphic artist - select graphic artist | [5 empty] | 11
11 | Finance/Legal | Bank/SBA lending - find banks that have financed restaurant startups | [5 empty] | 11
11 | Finance/Legal | Business plan - begin drafting your business plan | [5 empty] | 11
11 | Finance/Legal | Capital/construction/opening budget - estimate total startup cost of project through opening day - incorporate this into business plan - refer to Capital Budget worksheet on "Startup & Feasibility Spreadsheets" on RestaurantOwner.com | [5 empty] | 11
11 | Finance/Legal | List of possible names for restaurant - solicit ideas from friend, relatives | [5 empty] | 11
10 | Administration | Collect info on permits/licenses - health, liquor, other | [5 empty] | 10
10 | Administration | Insurance - identify requirements; building, liability, workmen's comp, other | [5 empty] | 10
10 | Concept | Further define concept - type of service, price range, menu | [5 empty] | 10
10 | Finance/Legal | Financial feasibility - begin establishing preliminary financial assumptions - sales, operating costs, capital costs, number of employees, etc. - refer to NRA's Industry Operation's Report for industry averages - use "Startup & Feasibility Spreadsheets" on RestaurantOwner.com | [5 empty] | 10
10 | Site/Planning | Facility requirements - how much space, seats, parking will you need | [5 empty] | 10
10 | Site/Planning | Site/location criteria - determine site/location criteria - demographics, traffic count - size, number of seats, rental rates - lease terms - other | [5 empty] | 10
9 | Concept | Points of difference - what will make your restaurant unique in terms of menu, service, ambiance, other | [5 empty] | 9
9 | Design/ Construction | List of architects - check references, create short list of quality firms | [5 empty] | 9
9 | Design/ Construction | List of general contractors - check references, create short list of quality firms | [5 empty] | 9
9 | Design/ Construction | List of interior design firms - check references, create short list of quality firms | [5 empty] | 9
9 | FF&E | Preliminary equipment requirements - create a list of the equipment needed | [5 empty] | 9
9 | Finance/Legal | Attorney & CPA - find firms with restaurant experience - get & check references | [5 empty] | 9
9 | Finance/Legal | Business entity - consider corporation, LLC, partnership, limited partnership - seek guidance from CPA/attorney | [5 empty] | 9
9 | Finance/Legal | Personal career accomplishments/work history - prepare and include in business plan | [5 empty] | 9
9 | Finance/Legal | Review financial projections with your CPA - have your CPA review for reasonableness, missing costs & expenses - have experienced restaurant professionals review your financials | [5 empty] | 9
9 | Finance/Legal | Select attorney - draft/file corporate documents - review/negotiate lease agreement | [5 empty] | 9
9 | Finance/Legal | Select CPA - determine corporate entity/review business plan financials | [5 empty] | 9
9 | Marketing | Competitive analysis - create list of competitors - obtain sample menus for research & reference | [5 empty] | 9
9 | Site/Planning | Competitive analysis - examine strengths & weaknesses of competitors in target areas - evaluate relative success of restaurant in local market - where is there potential? - what dining segments are not being well-served? | [5 empty] | 9
9 | Site/Planning | Square footage - determine optimum square footage needed (range) - including kitchen, dining room, storage - rule of thumb is roughly 30 square feet per seat (total square footage) | [5 empty] | 9
9 | Site/Planning | Tenent rep broker - secure service of a tenent rep broker to assist you in site selection - find a broker with a specialty or focus on restaurant sites | [5 empty] | 9
8 | Concept | Concept validation/testing - interview potential customers on your concept plans | [5 empty] | 8
8 | Concept | Determine name of restaurant - trade name search (attorney) | [5 empty] | 8
8 | Concept | Finalize concept - menu, service, unique offerings, price range, ambiance, etc. - draft concept statement fully describing concept | [5 empty] | 8
8 | Design/ Construction | Ansul system - what are local requirements | [5 empty] | 8
8 | Design/ Construction | Construction & development costs - get estimates of buildout/construction costs from contractors | [5 empty] | 8
8 | Design/ Construction | Exits - panic hardware requirements, emergency lighting - fire code requirements | [5 empty] | 8
8 | Design/ Construction | Handicap access/requirements | [5 empty] | 8
8 | FF&E | Equipment lists - kitchen, bar, dining room, bar, office | [5 empty] | 8
8 | FF&E | Lease or purchase kitchen equipment - shop equipment leasing companies | [5 empty] | 8
8 | Finance/Legal | Business plan - complete business plan | [5 empty] | 8
8 | Finance/Legal | Capital/construction/opening budget - update projections with actual bids/current estimates | [5 empty] | 8
8 | Finance/Legal | Personal financial statement - prepare / update your personal financial statement | [5 empty] | 8
8 | Operations | Visit restaurants with similar offerings - take notes of good & bad items | [5 empty] | 8
8 | Site/Planning | Bar seating - estimate potential for bar revenue - balance with space/seating needed for dining room | [5 empty] | 8
8 | Site/Planning | Building/fire/safety codes - obtain all applicable code requirements | [5 empty] | 8
8 | Site/Planning | Electrical service - evaluate adequacy of available power | [5 empty] | 8
8 | Site/Planning | Floor plan (existing space) - obtain floor plan of space - include layout of load-bearing (permanent) walls | [5 empty] | 8
8 | Site/Planning | Floor slope evaluation - consider slope on handicap, OSHA requirements - safety considerations for staff & guests | [5 empty] | 8
8 | Site/Planning | Lighting fixtures - inspect interior & exterior lighting including parking lot | [5 empty] | 8
8 | Site/Planning | Liquor license - know the process & cost of obtaining a liquor license | [5 empty] | 8
8 | Site/Planning | List of existing kitchen equipment - obtain detailed list - verify & evaluate condition | [5 empty] | 8
8 | Site/Planning | Number of tables/seats - estimate potential seating/revenue potential of dining room | [5 empty] | 8
8 | Site/Planning | Parking - is there adequate parking - what is the ratio of seats to parking spaces, is there a local minimum | [5 empty] | 8
8 | Site/Planning | Sales to investment analysis - estimate total capital costs & compare to projected annual sales - goal is to have minimum 1.5 to 1 sales to investment ratio in leasehold - goal is to have minimum 1 to 1 ratio when land & building is owned - go to RestaurantOwner.com for more information | [5 empty] | 8
8 | Site/Planning | Traffic patterns - evaluate adequacy of traffic flow (foot traffic, if applicable) | [5 empty] | 8
8 | Site/Planning | Zoning requirements - verity that there are no zoning problems with your concept/plans | [5 empty] | 8
7 | Administration | Banking - open construction/development account | [5 empty] | 7
7 | Administration | Liquor license - investigate application process/availability of liquor license | [5 empty] | 7
7 | Design/ Construction | Architectural/design - review & approve | [5 empty] | 7
7 | Design/ Construction | Builder's risk insursnce | [5 empty] | 7
7 | Design/ Construction | Contractor - select contractor | [5 empty] | 7
7 | Design/ Construction | Demolition work | [5 empty] | 7
7 | Design/ Construction | Design-Exterior - siding, ramps, windows, awnings, lighting | [5 empty] | 7
7 | Design/ Construction | Design-Interior - kitchen, bar, dining room, bar, office, lighting | [5 empty] | 7
7 | Design/ Construction | General liability insurance | [5 empty] | 7
7 | Design/ Construction | Patio / outside seating - design, available seating, permits, w/w station, cost feasibility | [5 empty] | 7
7 | Design/ Construction | Select architect/designer | [5 empty] | 7
7 | FF&E | Exterior signage - get local code/permit/approval requirements | [5 empty] | 7
7 | Finance/Legal | Buy-sell agreement - attorney prepares if you have partners/investors - consider insurance to fund | [5 empty] | 7
7 | Finance/Legal | Landlord approvals - determine what items require landlord approval - plans, signage, other | [5 empty] | 7
7 | Design/ Construction | Utilites billing changes - change name/party responsible for utility bills - electrical, gas, water | [5 empty] | 7
7 | Design/ Construction | Utilities - determine utility company options - choose provider | [5 empty] | 7
7 | Operations | Menu & recipes - narrow menu offereings - create & test recipes - use distributor test kitchen if possible | [5 empty] | 7
7 | Site/Planning | Cleanup required - determine cost of cleanup/demolition prior to construction activities | [5 empty] | 7
7 | Site/Planning | Gas main / lines - adequate size, capacity, age, condition | [5 empty] | 7
7 | Site/Planning | Health department - verify no health-related conditions present that could pose problems | [5 empty] | 7
7 | Site/Planning | HVAC system - inspect/evaluate condition | [5 empty] | 7
7 | Site/Planning | Plans for location/site area - inquire with local officials about proposed, planned projects in area - road, water, sewer, drainage, commercial, residential, zoning changes | [5 empty] | 7
7 | Site/Planning | Roof inspection | [5 empty] | 7
7 | Site/Planning | Sewer lines - evaluate adequacy; size, capacity, age, condition | [5 empty] | 7
7 | Site/Planning | Termite report - have property inspected for termite/pest problems | [5 empty] | 7
7 | Site/Planning | Type of flooring | [5 empty] | 7
7 | Site/Planning | Utility requirements - verify no utility/capacity problems | [5 empty] | 7
7 | Site/Planning | Water lines - evaluate capacity, size, age, condition | [5 empty] | 7
6 | Administration | Federal ID number - apply for | [5 empty] | 6
6 | Design/ Construction | Acoustical ceilings | [5 empty] | 6
6 | Design/ Construction | Air conditioning/circulation | [5 empty] | 6
6 | Design/ Construction | Back door - peep hole, buzzer for deliveries, emergency bar | [5 empty] | 6
6 | Design/ Construction | Bathroom partitions & accessories | [5 empty] | 6
6 | Design/ Construction | Burgler alarm system | [5 empty] | 6
6 | Design/ Construction | Canopies & awnings | [5 empty] | 6
6 | Design/ Construction | Carpentry | [5 empty] | 6
6 | Design/ Construction | Carpet | [5 empty] | 6
6 | Design/ Construction | Concrete | [5 empty] | 6
6 | Design/ Construction | Construction timeline - time for each phase, completion date | [5 empty] | 6
6 | Design/ Construction | Design elements - logo, colors, type style | [5 empty] | 6
6 | Design/ Construction | Door locks - deadbolts, re-key locks prior to opening | [5 empty] | 6
6 | Design/ Construction | Door/exits hardware - alarms, push bars, emergency escape | [5 empty] | 6
6 | Design/ Construction | Doors & Windows | [5 empty] | 6
6 | Design/ Construction | Doors, frames & hardware | [5 empty] | 6
6 | Design/ Construction | Drywall | [5 empty] | 6
6 | Design/ Construction | Electrical/Lighting | [5 empty] | 6
6 | Design/ Construction | Exterior painting | [5 empty] | 6
6 | Design/ Construction | Hardwood flooring | [5 empty] | 6
6 | Design/ Construction | Interior painting | [5 empty] | 6
6 | Design/ Construction | Kitchen fire control - design & setup system | [5 empty] | 6
6 | Design/ Construction | List of inspectors - building, fire, electrical, plumbing, health | [5 empty] | 6
6 | Design/ Construction | Masonry | [5 empty] | 6
6 | Design/ Construction | Mechanical | [5 empty] | 6
6 | Design/ Construction | Parking lot - resurfacing, control access during construction | [5 empty] | 6
6 | Design/ Construction | Paving | [5 empty] | 6
6 | Design/ Construction | Plumbing | [5 empty] | 6
6 | Design/ Construction | Resilient flooring | [5 empty] | 6
6 | Design/ Construction | Roofing & waterproofing | [5 empty] | 6
6 | Design/ Construction | Select contractor - obtain bids - contractor prepares timeline/critical path for completion | [5 empty] | 6
6 | Design/ Construction | Smoke detectors - wire to alarm system | [5 empty] | 6
6 | Design/ Construction | Sound/music system | [5 empty] | 6
6 | Design/ Construction | Specialty items | [5 empty] | 6
6 | Design/ Construction | Sprinkler system - obtain requirements - have wired to alarm system | [5 empty] | 6
6 | Design/ Construction | Steel/railings | [5 empty] | 6
6 | Design/ Construction | Tile - kitchen, bathrooms, dining areas, wall and floor | [5 empty] | 6
6 | Site/Planning | Site selection decision - finalize site selection | [5 empty] | 6
5 | Administration | Credit application sheet - create for setting up new accounts, include references | [5 empty] | 5
5 | Design/ Construction | Electrical service - permits, procedures, plans, installation, inspection | [5 empty] | 5
5 | Design/ Construction | Gas service - permits, procedures, plans, installation, inspection | [5 empty] | 5
5 | Design/ Construction | Grease trap - permits, procedures, plans, installation, inspection | [5 empty] | 5
5 | Design/ Construction | Landscaping - design & bid contract | [5 empty] | 5
5 | Design/ Construction | Lighting for parking lot | [5 empty] | 5
5 | Design/ Construction | Waste water - permits, procedures, plans, installation, inspection | [5 empty] | 5
5 | Design/ Construction | Water service - Permits, procedures, plans, installation, inspection | [5 empty] | 5
5 | Finance/Legal | Tax ID numbers/accounts - apply for federal, state unemployment insurance, state sales tax | [5 empty] | 5
5 | Ongoing Services | Insurance agent - building, general liability, liquor liability, workman's comp, group medical | [5 empty] | 5
5 | Operations | Table mix & arrangement - determine mix of 2 top, 4 top, round, booths - determine booth / table positions, table numbers | [5 empty] | 5
4 | Administration | Liquor license - apply for - consider hiring firm to assist in processing application | [5 empty] | 4
4 | Design/ Construction | Water quality - test for hard water, take bids for water softening, filtration | [5 empty] | 4
4 | FF&E | Safe for office - determine type, bid & order | [5 empty] | 4
4 | Food & Beverage | List of available suppliers - create list of suppliers for food, beverages & supplies | [5 empty] | 4
4 | Marketing | Menu boards & pictures - determine type, design, order - pictures of key menu items bundled with side & beverage | [5 empty] | 4
4 | Marketing | Banners - NOW HIRING /COMING SOON / NOW OPEN | [5 empty] | 4
4 | Operations | Hours of operation - determine for each day/meal period | [5 empty] | 4
4 | Operations | Vending machines - cigarettes, pay phones, video games, other | [5 empty] | 4
4 | Personnel | Employee benefits - determine insurance coverage (medical, dental, life, disability) & eligibility - vacation, meals, comps, tuition reimbursement, other | [5 empty] | 4
4 | Personnel | Employee job descriptions - create for all staff & management positions - download templates on RestaurantOwner.com | [5 empty] | 4
4 | Personnel | Management team - start interviewing/selection process | [5 empty] | 4
4 | Personnel | Organizational chart - create organizational chart for restaurant | [5 empty] | 4
3 | Smallwares / Supplies | Uniforms - finalize design; kitchen, service, bar, host staffs, managers | [5 empty] | 3 | 12
3 | Administration | Employee meal policy - determine policy | [5 empty] | 3
3 | Administration | Employee timekeeping system - decide on stand alone, time cards, manual, POS | [5 empty] | 3
3 | Design/ Construction | Cleaning crew - bid & select vendor for initial & final clean | [5 empty] | 3
3 | Design/ Construction | Exterior signage - primary, handicap, reserved, valet, hours of operation, delivery times | [5 empty] | 3
3 | Design/ Construction | Supplier, contractor, sub-contractor contacts - create master phone & contact list with emergency numbers | [5 empty] | 3
3 | FF&E | Soda system installation - select vendor & set up installation date | [5 empty] | 3
3 | Finance/Legal | Line of credit - set up working capital line of credit with bank | [5 empty] | 3
3 | Food & Beverage | Beer - decide what bottled / draft beers to stock | [5 empty] | 3
3 | Food & Beverage | Food inventory - create master inventory list of all ingredients/products to stock | [5 empty] | 3
3 | Food & Beverage | Liquor - determine well/premium/super premium brands | [5 empty] | 3
3 | Food & Beverage | Liquor, beer & wine inventory - create inventory worksheets for taking physical inventories - download Inventory Worksheet template on RestaurantOwner.com | [5 empty] | 3
3 | Food & Beverage | Price menu - determine final price points on all menu items | [5 empty] | 3
3 | Food & Beverage | Standard recipe files - begin building recipe binder & laminated recipe card for menu items - prepare recipe cards for all batch recipes | [5 empty] | 3
3 | Food & Beverage | Wine - determine wines to stock | [5 empty] | 3
3 | Food & Beverage | Wine list - design & print - include in main menu? | [5 empty] | 3
3 | Marketing | Gift certificates - design & print - program gift certificate sales keys into POS (both sale & redemption) | [5 empty] | 3
3 | Marketing | Local charities - choose which charity(s) to support - consider a "charity night" pre-opening party | [5 empty] | 3
3 | Marketing | Printing - stationary, envelopes, labels, business cards - invitations for opening parties | [5 empty] | 3
3 | Marketing | Public relations for opening - hire local PR firm - send out press releases to local media outlets | [5 empty] | 3
3 | Marketing | Yellow page ad - determine if yellow page advertising makes sense - inquire about timing of next printing cycle | [5 empty] | 3
3 | Ongoing Services | Dining room cleaning - carpet, flooring, rest rooms - select outside vendor | [5 empty] | 3
3 | Ongoing Services | Hood/kitchen cleaning - select approved vendor | [5 empty] | 3
3 | Ongoing Services | Interior plant service - select approved vendor | [5 empty] | 3
3 | Ongoing Services | Landscaping/lawn services - select approved vendor | [5 empty] | 3
3 | Ongoing Services | Security guards - determine if needed on certain nights/hours | [5 empty] | 3
3 | Operations | Checklists - prepare opening, closing, shift change checklists for all stations - download checklist templates on RestaurantOwner.com | [5 empty] | 3
3 | Operations | Guest (table ready) call system - determine system to use - pagers, sound system, other | [5 empty] | 3
3 | Operations | Happy hour - determine special, prices, food - check state/local laws regarding happy hour/discount programs | [5 empty] | 3
3 | Operations | Menu analysis - determine items for signature or high promotion status - base decision on gross profit margin, ease of preparation, quality | [5 empty] | 3
3 | Operations | Menu item cost - calculate raw food cost on all menu items - rank each categorie's items by gross profit margin - does prime distributor have food management software if so, ask for assistance | [5 empty] | 3
3 | Operations | Prep lists with pars - create prep lists with par levels | [5 empty] | 3
3 | Operations | Product specs - create detailed product specs for all food products - grade, size, packaging, brand, etc. - ask your distributor for assistance | [5 empty] | 3
3 | Operations | Reservation policy - determine if you will take reservations or not - consider "call in" program to place names on wait list only | [5 empty] | 3
3 | Operations | Station setup sheets with pars - for kitchen & dining room(s) | [5 empty] | 3
3 | Operatons | Customer comment cards - design & print - create procedures for receiving & responding - download template on RestaurantOwner.com | [5 empty] | 3
3 | Personnel | Employee handbook - create to document and communicate all employee & employment practices - download template on RestaurantOwner.com | [5 empty] | 3
3 | Personnel | Employee training manuals - create for all positions - download templates on RestaurantOwner.com | [5 empty] | 3
3 | Personnel | Management training materials - personnel hiring, training & management - operations - administrative | [5 empty] | 3
3 | Personnel | Master training schedule - create schedule for staffing training leading up to opening day | [5 empty] | 3
3 | Personnel | Sidework procedures & schedules - create server/front-of-house sidework checklists - download template on RestaurantOwner.com | [5 empty] | 3
3 | Personnel | Staff pay scales - determine starting pay scales for each position - determine employee review/raise policies | [5 empty] | 3
3 | Personnel | Staffing needs - determine number of new hires needed by position - plan for turnover, hire 20% more than you think you need | [5 empty] | 3
3 | Technology | POS phone line - dedicated line for charge approvals - tie into DSL/cable line | [5 empty] | 3
3 | Technology | POS system - list requirements - download POS Evaluation Worksheet on Restaurantowner.com - create list of brands/dealers used by other local operaters - start evaluation/demonstration process | [5 empty] | 3
3 | Technology | Website - register domain name - contact web design firm | [5 empty] | 3
2 | Administration | Alcoholic beverage server certification - determine requirements | [5 empty] | 2 | 8
2 | Administration | Tax permits - apply for Sales Tax ID (state, local) | [5 empty] | 2 | 8
2 | Smallwares/ Supplies | Dining room - high chairs - infant cradles - booster seats - water pitchers, wine carafes - serving trays, tray stands |  |  |  | 1 | 3
2 | Smallwares/ Supplies | Bar - blender - ice machine - glass washer - shakers, strainers, spoons, bottle openers, corkscrew - jiggers - scoops - bar mats - pitchers
2 | FF&E | Communications/phone system - phone lines for office, fax, kitchen, hostess station - pagers, cell phones, fire & burglar alarms - internet access, service provider | [5 empty] | 2 | 8
2 | FF&E | Interior signs - menu boards, restrooms, fire exit, hand wash, wait to be seated | [5 empty] | 2 | 8
2 | FF&E | Office equipment - copier, fax, computer, printer, calculators | [5 empty] | 2 | 8
2 | FF&E | Office furniture - desk, chairs, filing cabinet, shelving | [5 empty] | 2 | 8
2 | FF&E | Receiving scale - minimum 200lb capacity | [5 empty] | 2 | 8
2 | Food & Beverage | HACCAP training / certification - determine local/state certification requirements - arrange for manager/employee certification | [5 empty] | 2 | 8
2 | Ongoing Services | Payroll processing - outsource to ADP, Paychex, other | [5 empty] | 2 | 8
2 | Smallwares/ Supplies | Dishroom items - bus carts, bus tubs, glass racks, tray racks - chemicals, detergents | [5 empty] | 2 | 8
2 | Smallwares/ Supplies | Smallware & kitchen utensils - source, specs, bid order | [5 empty] | 2 | 8
2 | Smallwares/ Supplies | Tabletop items - tableware, flatware, glassware, sugar caddies, table tents, vases - salt & pepper shakers | [5 empty] | 2 | 8
2 | Administration | Banking - open operating, payroll, reserve accounts - order checks, deposit slips | [5 empty] | 2 | 7
2 | Administration | Payroll processing - in-house, outsource to ADP, Paychex, outside accountant | [5 empty] | 2 | 7
2 | Ongoing services | Music - Muzak, ASCAP, BMI (music licensing) - satellite radio | [5 empty] | 2 | 7
2 | Operations | Emergency exit procedures - determine procedures, post maps - discuss in safety meetings with staff | [5 empty] | 2 | 7
2 | Personnel | Employee recruiting - newspaper ads, "NOW HIRING" banner - recruiting missions - word of mouth campaigns - bonus for referrals - plan for turnover, hire 20% more than you think you need | [5 empty] | 2 | 7
2 | Personnel | Pre-opening interview site - trailer, temporary office - equip with phone, furniture, hiring/selection forms | [5 empty] | 2 | 7
2 | Technology | Computer software - Microsoft office, scheduling, food management | [5 empty] | 2 | 7
2 | Technology | POS system - make POS decision - set up menu items & prices - decide on comps & discount categories - set up essential reports | [5 empty] | 2 | 7
2 | Administration | Credit card merchant accounts - setup for MC/Visa, Amex, Discover, Others | [5 empty] | 2 | 6
2 | Design/Constr. | Building & equipment plans - retain full set of plans for operational files | [5 empty] | 2 | 6
2 | Design/Constr. | Walk-through with contractor - create initial punch list | [5 empty] | 2 | 6
2 | FF&E | Restrooms - hand towel/dryer dispensers, soap dispensers, hand soap, baby changing tables | [5 empty] | 2 | 6
2 | Food & Beverage | Menus - covers & inserts, to-go, catering, children's | [5 empty] | 2 | 6
2 | Ongoing Services | Chemicals - select approved vendor | [5 empty] | 2 | 6
2 | Ongoing Services | Grease trap - select approved vendor | [5 empty] | 2 | 6
2 | Ongoing Services | Knife & blade sharpening - perform in-house - use outside service | [5 empty] | 2 | 6
2 | Ongoing Services | Monthly accounting - determine monthly or 4-week cycle - use industry standard chart of accounts - outside accounting service or in-house bookkeeper/accountant | [5 empty] | 2 | 6
2 | Ongoing Services | Pest control - select approved vendor | [5 empty] | 2 | 6
2 | Ongoing Services | Trash disposal - select approved vendor | [5 empty] | 2 | 6
2 | Ongoing Services | Window washing - do in-house or outsource - select approved vendor | [5 empty] | 2 | 6
2 | Operations | Bulletin board - for employee schedule, mandadory postings - choking poster - emergency hospital & doctor numbers & instructions | [5 empty] | 2 | 6
2 | Operations | Children's amenities - menu, crayons, coloring book, high chairs, booster seats, balloons | [5 empty] | 2 | 6
2 | Operations | Cleaning & maintenance schedules - set up schedules & procedures - download Cleaning Checklists on RestaurantOwner.com | [5 empty] | 2 | 6
2 | Operations | Emergency numbers - map, directions to hospital - make arrangements with local doctor, clinic | [5 empty] | 2 | 6
2 | Operations | Entertainment - obtain permits if required - create list of potential entertainers | [5 empty] | 2 | 6
2 | Operations | Floor maintenance - get ongoing floor maintenance procedures - purchase cleaning / polishing supplies | [5 empty] | 2 | 6
2 | Operations | Valet parking - valet stand - key control system - valet only parking area signs, cones | [5 empty] | 2 | 6
2 | Personnel | Food safety training - purchase food safety training materials/videos - contact state or National Restauant Association | [5 empty] | 2 | 6
2 | Smallwares/ Supplies | Employee name tags | [5 empty] | 2 | 6
2 | Technology | Phone on hold message - select service provider - message/music | [5 empty] | 2 | 6
2 | Administration | Accounting software - if accounting done in-house; Quickbooks, Peachtree, other - format P&L consistent with NRA Uniform System of Accounts | [5 empty] | 2 | 5
2 | Administration | Petty cash - setup petty cash fund for cash payments - create petty cash reimbursement form | [5 empty] | 2 | 5
2 | Design/ Construction | Compressors & valves - label and check for accessibility | [5 empty] | 2 | 5
2 | Design/ Construction | Electrical labeling - label switches, breakers and check for accessibility | [5 empty] | 2 | 5
2 | FF&E | Janitorial equipment - wet floor signs, mops, buckets, vacuum - trash cans, cordless dust pan | [5 empty] | 2 | 5
2 | Ongoing Services | Armored car service - select approved vendor | [5 empty] | 2 | 5
2 | Ongoing Services | Building & HVAC repairs - select approved vendors | [5 empty] | 2 | 5
2 | Ongoing Services | Dishwasher service - select approved vendor | [5 empty] | 2 | 5
2 | Ongoing Services | Laundry & linen - select approved vendor | [5 empty] | 2 | 5
2 | Operations | Approved vendor list - create Master Approved Vendor List - include primary & backup vendors | [5 empty] | 2 | 5
2 | Operations | Birthday specials - determine policy, special desserts, b-day song, other | [5 empty] | 2 | 5
2 | Operations | Seating chart & waitstaff sections - create seating chart diagram with waitstaff sections | [5 empty] | 2 | 5
2 | Personnel | Assemble new employee materials - application forms - uniforms - W-4, I-9 forms - employee handbook, job descriptions - orientation & training checklists - check RestaurantOwner.com for forms & templates | [5 empty] | 2 | 5
2 | Personnel | Employee files - set up for employment application, status changes, other personnel records | [5 empty] | 2 | 5
2 | Smallwares/ Supplies | First aid kit - emergency burn kit | [5 empty] | 2 | 5
2 | Smallwares/ Supplies | Tip trays, check presentation folders - may be free from AMEX/MC or VISA | [5 empty] | 2 | 5
2 | Administration | Deposit procedures - armored car service or other | [5 empty] | 2 | 4
2 | Design/ Construction | Inspections - schedule for fire, health departments | [5 empty] | 2 | 4
2 | Operations | Initial food, beverage & supplies orders - determine quantities for training, mock shifts, pre-opening activities | [5 empty] | 2 | 4
1 | Administration | Insurance - verify with your agent that all policies are in force | [5 empty] | 1 | 4
1 | Design/Constr. | Parking lot striping - handicap space requirements | [5 empty] | 1 | 4
1 | FF&E | Emergency equipment procedures - determine emergency shut-off steps - label equipment | [5 empty] | 1 | 4
1 | FF&E | Equipment tests - test each piece with supplier prior to training | [5 empty] | 1 | 4
1 | FF&E | Kitchen clock - purchase & install | [5 empty] | 1 | 4
1 | FF&E | Kitchen tools/toolkit - purchase & designate location store | [5 empty] | 1 | 4
1 | Food & Beverage | Initial food order - prepare & place initial order - request free samples from suppliers to test - have sufficient quantites for testing & training | [5 empty] | 1 | 4
1 | Food & Beverage | Photographs of menu items - for display in kitchen area | [5 empty] | 1 | 4
1 | Marketing | Opening party(s) - press event, VIPs, contractors & suppliers - create guest lists, send invitations | [5 empty] | 1 | 4
1 | Personnel | OSHA - review OSHA standards with managers | [5 empty] | 1 | 4
1 | Smallwares/ Supplies | Initial chemicals order - degreasers, drain treatment - disinfectants, sanitizers - floor care solutions - handcare - cleaners for dishroom/restroom/dining room | [5 empty] | 1 | 4
1 | Smallwares/ Supplies | Linen - table cloths, napkins, bar & kitchen towels | [5 empty] | 1 | 4
1 | Technology | Internet service provider - DSL or cable | [5 empty] | 1 | 4
1 | Administration | Bank supplies - deposit stamp & pad, deposit bags, deposit slips | [5 empty] | 1 | 3
1 | Design/ Construction | Alarm system - install & inspect | [5 empty] | 1 | 3
1 | Design/ Construction | Beverage service - set up installation of post mix system, coffee, iced tea | [5 empty] | 1 | 3
1 | Design/ Construction | Fire extinguishers - install with visible operating instructions | [5 empty] | 1 | 3
1 | FF&E | Ansul system - inspect | [5 empty] | 1 | 3
1 | FF&E | R&M binder for all equipment - prepare repair & maintenance binder for operating instructions, manuals - mail in warranty cards | [5 empty] | 1 | 3
1 | FF&E | Storage shelves - clean, organize & label; walk-in, freezer, dry storage | [5 empty] | 1 | 3
1 | Operations | Order & delivery schedule - prepare weekly schedule with each vendor's order & deliver dates - download "Ordering & Receiving Schedule" template on RestaurantOwner.com | [5 empty] | 1 | 3
1 | Operations | Padlocks for cooler doors - create control system for access & keys - limit access to storage rooms to deliveries & requisition into production | [5 empty] | 1 | 3
1 | Personnel | Alcoholic beverage server certification - determine state/local requirements - assign employee(s) for certification course | [5 empty] | 1 | 3
1 | Personnel | HACCAP training / certification - assign employee(s) for certification course | [5 empty] | 1 | 3
1 | Personnel | Safety checklist & audit - create safety checklist & perform safety audit - download Safety Checklist template on RestaurantOwner.com | [5 empty] | 1 | 3
1 | Personnel | Wine training program - arrange for wine supplier to provide | [5 empty] | 1 | 3
1 | Smallwares/ Supplies | Initial paper good order - napkins, take-out, delivery, coasters, doggie bags - straws, cups, lids - filters, butcher pager - patty paper, food wrap film, aluminum foil | [5 empty] | 1 | 3
1 | Smallwares/ Supplies | Janitorial supplies - carpet, tile, floor cleaner, spot remover - gum solvent, liquid hand soap, paper towels, toilet paper | [5 empty] | 1 | 3
1 | Technology | POS/register - set up installation & training | [5 empty] | 1 | 3
1 | Administration | Accounting/bookkeeping system - have CPA review sales, deposit, payroll and accounts payable system | [5 empty] | 1 | 2
1 | Administration | Permits, licenses, inspections, approvals - verify that licenses, etc. have been secured | [5 empty] | 1 | 2
1 | Design/ Construction | Exterior signage light timer - set light timer | [5 empty] | 1 | 2
1 | Design/ Construction | Update construction punch list | [5 empty] | 1 | 2
1 | FF&E | Calibrate temperatures on equipment - fryers, griddle, oven, stove, other | [5 empty] | 1 | 2
1 | FF&E | Check walk-in & refrigeration temperatures | [5 empty] | 1 | 2
1 | FF&E | Clean & sanitize walk-in, freezer | [5 empty] | 1 | 2
1 | FF&E | Receive furniture - tables, chairs, desk tops, benches, patio furniture | [5 empty] | 1 | 2
1 | FF&E | Test all equipment | [5 empty] | 1 | 2
1 | Food & Beverage | Initial alcoholic beverage order - prepare & place initial order | [5 empty] | 1 | 2
1 | Operations | Deposit bags - obtain from bank | [5 empty] | 1 | 2
1 | Operations | Hostess stand supplies - reservation book, call clock, pencils, notebooks, kid's stuff | [5 empty] | 1 | 2
1 | Operations | Light levels - determine for each meal period - label light switches | [5 empty] | 1 | 2
1 | Personnel | Begin staff training | [5 empty] | 1 | 2
1 | Personnel | Safety & first aid training - conduct training program for all employees | [5 empty] | 1 | 2
1 | Administration | Initial change order - get change & small bills from bank | [5 empty] | 1 | 1
1 | Administration | POS/merchant accounts - test credit card approval/processing | [5 empty] | 1 | 1
1 | Administration | Receive certificate of occupancy | [5 empty] | 1 | 1
1 | Design/Constr. | Continue construction punch list | [5 empty] | 1 | 1
1 | Design/ Construction | Exterior cleanup - parking lot, landscaping, building, windows | [5 empty] | 1 | 1
1 | Design/ Construction | Final clean - interior & exterior of building | [5 empty] | 1 | 1
1 | Design/ Construction | Wash windows | [5 empty] | 1 | 1
1 | FF&E | Complete equipment warranty cards | [5 empty] | 1 | 1
1 | FF&E | Final clean all equipment | [5 empty] | 1 | 1
1 | FF&E | Hang pictures, wall decore | [5 empty] | 1 | 1
1 | FF&E | Install interior plants | [5 empty] | 1 | 1
1 | FF&E | Run ice machine - empty/sanitize/refill - find ice company for backup | [5 empty] | 1 | 1
1 | Operations | Change order - prepare initial change order; change & small bills | [5 empty] | 1 | 1
1 | Operations | Check inventory levels - on all food, beverage, paper & supplies - prepare orders for opening week | [5 empty] | 1 | 1
1 | Operations | Opening inventory - take full physical inventory on all food & beverage items night before opening - necessary to calculate accurate food & beverage costs after opening | [5 empty] | 1 | 1
1 | Personnel | Conduct practice runs/mock service - full dress with uniforms | [5 empty] | 1 | 1
1 | Personnel | Finalize opening week employee schedules - staff heavy - plan for turnover, no-shows | [5 empty] | 1 | 1
1 | Ongoing Services | Equipment repairs - select approved vendors
Note on A4: Guidelines to begin/complete this activity prior to scheduled opening day.
Note on AC4: Guidelines to begin/complete this activity prior to scheduled opening day.